## POD-40LPD-plan
Scope Of the project | Automation of 36K AWG, Intelleigent water sysytem, Data capturing, Display data, control ref system, Water level in tank |  |  | Schedule
Project description | Automation of 36K AWG
Project Owner | Sk. Hasem Ali
CFT | Hasem, Amit Bose, Bappa
Revision | A
Updated on | 2019-01-09
Activity | Responsible | Target Date | Schedule | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W11 | W12 | W13 | W14 | W16 | W16
Undestant the project scope | Hasem, Amit Bose, Bappa, Shaikh | 2019-01-09 | Plan
Actual
Schematic diagram for system | Hasem, Amit | 2019-01-12 | Plan
Actual
Prepare Bill of material | Hasem, Amit | 2019-01-12 | Plan
Actual
Wiring Diagram | Hasem, Amit | 2019-01-15 | Plan
Actual
Material procurement | Hasem/Pamela | 2019-01-19 | Plan
Actual
Components assembly with wiring | Hasem, Bappa | 2019-01-26 | Plan
Actual
Programming micro controller | Hasem | 2016-02-09 | Plan
Actual
Components placement in the machine | Hasem, Bappa | 2019-02-16 | Plan
Actual
Updating Schematic diagram of system according to new features | Hasem, Amit, Shaikh | 2019-02-23 | Plan
Actual
Updating Wiring diagram of system according to new features and preparing BOM for new features | Hasem, Amit | 2019-03-02 | Plan
Actual
Material procurement and connecting components | Hasem, Pamela, Bappa | 2019-03-09 | Plan
Actual
Adding feature to the existing system | Hasem, Amit, Bappa | 2019-03-16 | Plan
Actual
Testing | Shaikh, Hasem | 2019-03-16 | Plan
Actual
PCB design | Hasem, Amit | 2019-04-06 | Plan
Actual
Material procurement | Hasem, Pamela | 2019-04-06 | Plan
Actual
Receive PCB board from supplier | Hasem, Pamela | 2019-04-13 | Plan
Actual
Soldering components to PCB | Hasem, Bappa | 2019-04-20 | Plan
Actual
Placement of PCB inside AWG | Hasem, Bappa, Alok | 2019-04-27 | Plan
Actual
Testing | Shaikh, Hasem | 2019-05-25 | Plan
Actual